## Sheet1
Month | Phases | Tasks | Brief Description | Deadline
November | Requirements Gathering | Create Survey | Aimed at collecting participants' opinions of one good and one bad manners in the country they live | 17th November
|  | Open Survey and Send out to Participants | Survey will be sent out to participants to fill, in order to determine which cultures will be added within the study | 19th November
|  | Create wireframes of the page templates | Draw up a rough sketch of the pages - the layout of the pages, the flow and features the pages may include | 21st November
|  | Close the survey | Respondents shouldn't be able to submit answers. Hopefully there's a substantial amount of data | 26th November
| System Development | Begin coding the application | The main home page will, at least, start being worked on here. Perhaps create a template html page for the other pages - disussion forum, quiz and tutorial pages | 30th November
December |  | Write and include unit testing | Depending on what elements and features have been included within the application, they would be tested here | 13th December
| User Testing | Conduct first set of user testing | Participants should've been contacted and consent should have been given for testing to happen. A time should have been arranged. | 31st Decmber
January |  | Write up and document user testing results | Testing should have been completed. Results would be written and implemented within the documentation | 7th January
| System Development | Implement feedback from the testing | Feedback should be implemented within the code, depending on results given. | 14th January